# Task List — Hayk Manukyan, CBDO (Operations Lead)

August 7, 2026 · Sorted by priority. Format: task → deadline → done-criterion.

## Critical (launch-blocking)

- Cemetery agreement oversight. First operator contact ≤ Aug 13; status report Aug 20. Done: framework agreement or the operator's written position (executed by counsel; CBDO escalates — including an in-person visit — if unanswered).

- Contractor signatures. By Aug 8. Done: designer and developer agreements signed; IP transfers on milestone payments; source files an acceptance condition.

- Real site contacts. This week. Done: working phone number and info@memorycare.am replacing placeholders.

- Accountant hire. By Aug 20. Done: accountant onboarded with the task list (Document 12); until then, primary documents archived with counsel.

- Foreign-card payment test (with the CEO and developers). As soon as the bank enables acquiring. Done: a US/EU card payment completes end to end.

## High priority

- Hire two pilot technicians per the recruitment materials (Document 16). By end of August. Done: two candidates selected; formal employment prepared (start follows the cemetery resolution).

- Protocol training (Document 15) plus two rehearsal visits. Done: rehearsal reports pass review without corrections.

- September paid pilot: 5–10 full-price visits, crew of CBDO + two technicians, 1–2 diaspora clients. Done: 3+ publishable cases, 2+ testimonials, 1+ diaspora; actual visit times and consumables logged.

- Freelancer price collection (5–10 quotes, as a customer). Before the pilot. Done: anchor table for marketing.

- Pilot debrief with the CEO: field unit costs versus model, Maximum-tier margin, decisions on "pay after first report" and the Express display role.

## Medium priority

- Organic seeding across diaspora communities post-pilot (ready lists and posts; 3–4 communities/day, language-matched).

- Partnership outreach: five letters (churches in LA/Marseille/Moscow, AGBU network, diaspora media) → one confirmed partnership.

- Weekly Monday numbers review from soft launch onward (sales, CAC by channel, crew utilization, report quality).

- Seasonal calendar execution (Merelots, Easter, Vardavar, April 24, New Year) — preparation three weeks ahead of each date.

- Kill-criterion monitoring: fewer than 40 paying clients by month 4 post-launch → convene the rebuild review with the CEO.