# Task List — David Hambardzumyan, CEO (Owner)

August 7, 2026 · Sorted by priority.

## Critical

- Ameriabank. Corporate account plus internet-acquiring application. Cover explicitly: acceptance of foreign Visa/MC (US/EU/RU), foreign-card fees, chargeback procedure and statistics, onboarding timeline, merchant requirements, 3-D Secure, Apple Pay/Google Pay. Done: account open, acquiring application filed, timeline known.

- First funding tranche as required. Model v6.0 peak requirement ≈ AMD 5.0M with reserves; near-term outflows: contractor milestones (AMD 2.2M), content production AMD 500K (months 1–3), insurance and the AMD 500K incident reserve. Done: tranche schedule agreed with the CBDO against the payment calendar.

- Countersign contractor agreements. By Aug 8.

## High priority

- Vehicle lease agreement (personal vehicle → company) at a market rate, per counsel's draft; decide purchase timing against the pilot date.

- Software subscription transfer from the personal card to the company account once banking is live; provide payment history to the accountant for reimbursement processing.

- Kill criterion (adopted): confirm shared understanding — fewer than 40 paying clients by month 4 post-launch means stop and rebuild together, not automatic top-up funding.

## Medium priority

- Join the pilot debrief (late September): field unit costs, Maximum-tier margin, "pay after first report," Express display role.

- Year-2 decision on launching the QR digital memorial (separate, owner-level decision).

- End of Year 2: the VAT-transition pricing decision for Year 3 (pass-through of ~8–15% versus absorption).