# Task List — Legal Counsel

August 7, 2026 · Sorted by priority.

## Critical

- Cemetery operator — framework agreement (adopted: target an agreement, not a letter). First contact ≤ Aug 13; status report Aug 20. Must address: (a) the right of a commercial crew to work on a family's instruction; (b) any operator exclusivity or concession; (c) vehicle entry and parking; (d) water access; (e) waste removal; (f) photo/video filming; (g) status relative to caretakers and informal workers. If unanswered beyond two weeks — an in-person visit with the founders.

- Contractor agreements to signature by Aug 8. Required terms: milestones and acceptance procedure; exclusive rights to code/designs/source files transferring with each milestone payment (not only on full payment); repository and design-file handover as an acceptance condition; retroactive coverage of work already performed; staged payments; a pause option pending the cemetery resolution.

- Tax memorandum by Aug 13 (one page, written): applicability of the 10% turnover regime; the AMD 115M VAT threshold and transition mechanics; fiscal-receipt requirements for online card payments from abroad; a preliminary position on revenue recognition for annual prepayments (cash versus deferred) pending the accountant.

## High priority

- Liability insurance before the pilot (damage to property and adjacent graves during works); document the AMD 500K incident reserve by owner resolution.

- Platform legal pack before the first payment: public terms of service for US/EU clients (pro-rata refunds, 14-day withdrawal, renewal only with explicit consent, governing law); privacy policy in English; Family Circle sub-account consents (accepted at first login); filming rules — third-party graves and visitors never in frame; blurring in marketing materials.

- Vehicle lease agreement (owner's personal vehicle → company) at a documented market rate (related-party).

- Employment templates for field staff before hiring; formal registration precedes any field day, including paid trial days; salaries documented as net with payroll computed by the accountant.

## Medium priority

- Primary-document archive for all company spending until the accountant starts (Aug 20), then handover.

- A short written client agreement for the pilot (5–10 full-price visits).

- Trademark advice: registrability of MemoryCare and the slogan in Armenia; report by month end.